## Sheet1
User Story | points
As a user, I can register with a username and password | 1 | Total Points: 35 points
As the system, I reject registration attempts for usernames that already exist | 1
As a user, I can login with a username and password | 2
As the system, I reject login attempts with invalid credentials | 1
As a customer, I can apply for a new bank account with a starting balance. | 3
As a customer, I can view the balance of a specific account | 1
As a customer, I can make a deposit to a specific account | 2
As a customer, I can make a withdrawal from a specific account | 2
As the system, I reject and prevent overdrafts | 1
As the system, I reject deposits or withdrawals of negative money | 2
As the system, I reject any transactions of unapproved accounts | 1
As an employee, I can approve or reject an account. | 2
As a customer, I can post a money transfer to another account. | 3
As the system, I reject invalid transfers (negative amounts or overdrafts) | 1
As an employee, I can view a log of all transactions. | 2
File I/O integration tests | 10
Must Have | Compulsory
Good To Have / Nice to Have | Optional
Should Have | Important
Database integration tests
NOTE: database tests are ignored for scoring purposes, but you should still run the tests locally to help you validate your JDBC code

## Sprint1
Req_ID | UserStory | Points | Status
InProgress/Completed/Bug
| As a user, I can register with a username and password | 1
| As the system, I reject registration attempts for usernames that already exist | 1
| As a user, I can login with a username and password | 2
| As the system, I reject login attempts with invalid credentials | 1
| As a customer, I can apply for a new bank account with a starting balance. | 3
| As a customer, I can view the balance of a specific account | 1
| As a customer, I can make a deposit to a specific account | 2
| As a customer, I can make a withdrawal from a specific account | 2
| As the system, I reject deposits or withdrawals of negative money | 2
| As the system, I reject and prevent overdrafts | 1